## FMEA template
FMEA Template
| Process Name: |  |  | Date Created: |  |  | Version #:
| Process Owner: | [5 empty] | Last revision date:
Sr # | Process Step/Input | Potential Failure Mode | Potential Failure Effects | SEVERITY (1 - 10) | Potential Causes | OCCURRENCE (1 - 10) | Current Controls | DETECTION (1 - 10) | RPN | Action Recommended | Resp. | Target date | Actions Taken | SEVERITY (1 - 10) | OCCURRENCE (1 - 10) | DETECTION (1 - 10) | REVISED RPN
| What is the process step? | In what ways could the step go wrong? | What is the impact on the customer if this failure is not prevented or corrected? |  | What causes the stepto go wrong? (Ask why to the potential Failure mode) |  | What controls exist that either prevent or detect the failure befiore it impacts the customer? |  |  | What are the recommended actions for reducing the occurrence of the cause or improving detection? | Who is responsible for making sure the actions are completed? | By when will the actions get implemented | What actions were actually completed
1 | Put water in the cup | Puts too less or too much | Taste of the coffee is bad | 5 | No standardized measurement system in place to determine the quntity of water | 8 | visual inspection of coffee quantify after water addition | 3 | 120 | Provide standard measuring cups for water | Ruben | 2020-12-04 | Provide standard measuring cups for water | 5 | 2 | 3 | 30
2

## Overview - FMEA scale
| Description | Low Number | High Number
Severity | Severity ranking encompasses what is important to the industry, company or customers (e.g., safety standards, environment, legal, production continuity, scrap, loss of business, damaged reputation) | Low impact | High impact
Occurence | Rank the probability of a failure occuring during the expected lifetime of the product or service | Not likely to occur | Inevitable
Detection | Rank the probability of the problem being detected and acted upon before it has happened | Very likely to be detected | Not likely to be detected

## Severity Scale
Severity Scale
Adapt as required
| Effect | Severity of Effect | Ranking
| Hazardous - Without Warning | May expose client to loss, harm or major disruption - failure will occur without warning | 10
| Hazardous - With Warning | May expose client to loss, harm or major disruption - failure will occur with warning | 9
| Very High | Major disruption of service involving client interaction, resulting in either associate re-work or inconvenience to client | 8
| High | Minor disruption of service involving client interaction and resulting in either associate re-work or inconvenience to clients | 7
| Moderate | Major disruption of service not involving client interaction and resulting in either associate re-work or inconvenience to clients | 6
| Low | Minor disruption of service not involving client interaction and resulting in either associate re-work or inconvenience to clients | 5
| Very Low | Minor disruption of service involving client interaction that does not result in either associate re-work or inconvenience to clients | 4
| Minor | Minor disruption of service not involving client interaction and does not result in either associate re-work or inconvenience to clients | 3
| Very Minor | No disruption of service noticed by the client in any capacity and does not result in either associate re-work or inconvenience to clients | 2
| None | No Effect | 1

## Occurrence Scale
Occurrence Scale
Adapt as required
| Probability of Failure | Time Period | Per Item Failure Rates | Ranking
| Very High: Failure is almost inevitable | More than once per day | >= 1 in 2 | 10
|  | Once every 3-4 days | 1 in 3 | 9
| High: Generally associated with processes similar to previous processes that have often failed | Once every week | 1 in 8 | 8
|  | Once every month | 1in 20 | 7
| Moderate: Generally associated with processes similar to previous processes which have experienced occasional failures, but not in major proportions | Once every 3 months | 1 in 80 | 6
|  | Once every 6 months | 1 in 400 | 5
|  | Once a year | 1 in 800 | 4
| Low: Isolated failures associated with similar processes | Once every 1 - 3 years | 1 in 1,500 | 3
| Very Low: Only isolated failures associated with almost identical processes | Once every 3 - 6 years | 1 in 3,000 | 2
| Remote: Failure is unlikely. No failures associated with almost identical processes | Once Every 7+ Years | 1 in 6000 | 1

## Detection Scale
Detection Scale
Adapt as required
| Detection | Criteria: Likelihood the existence of a defect will be detected by process controls before next or subsequent process, -OR- before exposure to a client | Ranking
| Almost Impossible | No known controls available to detect failure mode | 10
| Very Remote | Very remote likelihood current controls will detect failure mode | 9
| Remote | Remote likelihood current controls will detect failure mode | 8
| Very Low | Very low likelihood current controls will detect failure mode | 7
| Low | Low likelihood current controls will detect failure mode | 6
| Moderate | Moderate likelihood current controls will detect failure mode | 5
| Moderately High | Moderately high likelihood current controls will detect failure mode | 4
| High | High likelihood current controls will detect failure mode | 3
| Very High | Very high likelihood current controls will detect failure mode | 2
| Almost Certain | Current controls almost certain to detect the failure mode. Reliable detection controls are known with similar processes. | 1